## Week 1
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
2026-04-13 | Project Setup & Infrastructure | 1.1.1 | GitHub repository setup ◦ Create monorepo: /app (RN), /admin (React), /functions (Firebase) ◦ Set up .env.example for all secrets | Repo created with branch strategy: main / develop / feature/*. README with setup instructions. | Mobile Dev | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.1.2 | Firebase project creation ◦ Enable Google Sign-In provider in Auth ◦ Set Firestore security rules (authenticated access) ◦ Register SHA-1 fingerprint for Android | Firebase project active. Firestore, Auth, FCM, Storage, Functions enabled. Android & iOS apps registered. | Backend Dev | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.1.3 | React Native project init ◦ react-navigation v6 with bottom tab + stack navigators ◦ react-native-firebase installed and linked ◦ Splash screen and app icon configured with church branding | RN app runs on Android emulator and iOS simulator. Navigation stack installed. | Mobile Dev | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.1.4 | Salesforce Connected App ◦ Permissions: Contacts RW, Campaigns RW, Opportunities RW, Cases RW ◦ Custom fields: Mobile_App_ID__c on Contact, App_RSVP__c on Campaign Member | Connected App created in SF org. OAuth2 JWT Bearer configured. Test API call returns 200. | SF Admin | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.1.5 | PhonePe merchant account ◦ Business documents uploaded to PhonePe portal ◦ Use PhonePe sandbox keys for development during onboarding | PhonePe PG merchant onboarding application SUBMITTED (approval takes 2-3 weeks). | Backend Dev | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.1.6 | CI/CD pipeline ◦ GitHub Actions workflow: lint + unit test on every PR ◦ Fastlane lanes for TestFlight and Play Store internal track | GitHub Actions workflow: lint + unit test on every PR. Fastlane lanes for TestFlight and Play Store internal track. | Mobile Dev | P2 - Medium | Not Started
| Project Setup & Infrastructure | 1.2.1 | Figma component library ◦ Primary: #1a2d5a Accent: #c0392b Gold: #f0a500 ◦ Font: Inter (mobile) — matches church brand ◦ Export all icons as SVG and screen assets as PNG @1x/2x/3x | Design tokens defined: colours, typography, spacing, border radius. All 8 wireframe screens converted to high-fidelity Figma. | Designer | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.2.2 | Church branding assets ◦ iOS: icon.png 1024x1024 no alpha channel ◦ Android: Adaptive icon foreground + background layers ◦ Splash: 3 sizes for Android (hdpi/xhdpi/xxhdpi) | App icon (1024x1024), splash screen, notification icon delivered as production-ready assets. | Designer | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.2.3 | Figma prototype ◦ Clickable Figma prototype covering all 8 screens. | Clickable Figma prototype covering all 8 screens. Share link sent to church for approval. | Designer | P1 - High | Not Started
| Project Setup & Infrastructure | 1.3.1 | Collections schema defined ◦ users/{uid} ◦ dailyPromises/{date} ◦ dailyVideos/{date} ◦ events/{eventId} ◦ prayerRequests/{reqId} ◦ announcements/{id} ◦ givingTransactions/{txId} | Firestore collections created with seed data. Security rules tested. | Backend Dev | P0 - Critical | Not Started
| Project Setup & Infrastructure | 1.3.2 | Firestore indexes ◦ prayerRequests: (status, createdAt DESC) ◦ events: (date ASC) ◦ givingTransactions: (uid, createdAt DESC) | Composite indexes created for all query patterns used in the app. | Backend Dev | P1 - High | Not Started

## Week 2
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| Auth & Home Screen | 2.1.1 | Phone OTP login ◦ Auto-read OTP on Android ◦ Resend OTP countdown ◦ Error states handling | User enters mobile number, receives OTP via Firebase Auth SMS, verified and logged in. Works on Android & iOS. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.1.2 | Google Sign-In ◦ SHA-1 fingerprint registered ◦ GoogleService-Info.plist and google-services.json configured | Google OAuth flow works end-to-end on both platforms. User profile auto-populated from Google account. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.1.3 | Guest mode ◦ Guest can browse Home, Promise, Video, Events ◦ Prayer Wall and Give require sign-in | Guest can browse public areas. Prompted to login when accessing restricted areas. | Mobile Dev | P1 - High | Not Started
| Auth & Home Screen | 2.1.4 | Auth persistence ◦ Login state persists across app restarts | Auto-login on relaunch. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.1.5 | Firebase <-> Salesforce user sync ◦ Match on phone number first, then email ◦ Create or Update Contact | On first login, Cloud Function creates/updates Salesforce Contact via REST API. sfContactId stored in Firestore user doc. | Backend Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.2.1 | Welcome / splash screen ◦ Splash shows for 2.5 sec then auto-navigates | CG logo animates in. Church name and tagline visible. | Mobile Dev | P1 - High | Not Started
| Auth & Home Screen | 2.2.2 | Profile setup screen ◦ Cell groups loaded from Firestore ◦ Profile photo upload | After first login, user completes profile. Skippable. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.2.3 | Notification permission prompt ◦ iOS/Android native permission dialogs | After profile setup, system permission dialog shown with explanation of notifications. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.2.4 | Language selection (EN/TE) ◦ Toggle between Telugu and English | Language stored in AsyncStorage and user doc. | Mobile Dev | P2 - Medium | Not Started
| Auth & Home Screen | 2.3.1 | Personalized greeting ◦ Greeting based on time | Shows greeting with user Name and next upcoming event. | Mobile Dev | P1 - High | Not Started
| Auth & Home Screen | 2.3.2 | Today's promise card ◦ Offline caching ◦ Fetches today's verse | Displayed as navy card with verse + reference. Tappable to promise screen. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.3.3 | Quick action grid (2x2) ◦ Promise, Video, Prayer, Give | Four tappable cards navigating to respective screens. | Mobile Dev | P0 - Critical | Not Started
| Auth & Home Screen | 2.3.4 | Next event card ◦ Fetches next upcoming event | Shows date badge, title, time, venue, RSVP status. | Mobile Dev | P1 - High | Not Started
| Auth & Home Screen | 2.3.5 | Announcements strip ◦ Latest pinned announcement | Scrollable horizontally if multiple. | Mobile Dev | P1 - High | Not Started
| Auth & Home Screen | 2.3.6 | Bottom navigation bar ◦ 5 tabs | Active tab highlighted. Badge on Prayer for new responses. | Mobile Dev | P0 - Critical | Not Started

## Week 3
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| Promise & YouTube Video | 3.1.1 | Promise detail screen ◦ Full-screen verse card | Shows verse text, reference, date, Devotional note, pastor name. | Mobile Dev | P0 - Critical | Not Started
| Promise & YouTube Video | 3.1.2 | Share promise as image ◦ Capture card as image | Tapping Share generates a PNG image and opens native share sheet. | Mobile Dev | P0 - Critical | Not Started
| Promise & YouTube Video | 3.1.3 | Save to gallery ◦ Save image to device | Saved to photo library. Permissions handled. | Mobile Dev | P1 - High | Not Started
| Promise & YouTube Video | 3.1.4 | Promise archive ◦ Past 30 days stored | Scrollable list of past 30 days of promises. | Mobile Dev | P1 - High | Not Started
| Promise & YouTube Video | 3.1.5 | Bookmark promise ◦ Heart icon bookmark | Saved to user doc in Firestore. Accessible from profile. | Mobile Dev | P2 - Medium | Not Started
| Promise & YouTube Video | 3.1.6 | Daily promise push notification ◦ Cloud Scheduler cron | Push notification sent daily at user-configured time. | Backend Dev | P0 - Critical | Not Started
| Promise & YouTube Video | 3.1.7 | Admin: schedule promises ◦ Allow scheduling up to 60 days | Web admin portal allows pastor to create/edit daily promises. | Backend Dev | P0 - Critical | Not Started
| Promise & YouTube Video | 3.2.1 | YouTube video player ◦ Embedded player auto loads | Today's 1-min video embedded in-app using iframe. | Mobile Dev | P0 - Critical | Not Started
| Promise & YouTube Video | 3.2.2 | Video metadata display ◦ Below player meta data | Video title, pastor name, duration, date, Share, Subscribe. | Mobile Dev | P1 - High | Not Started
| Promise & YouTube Video | 3.2.3 | Subscribe to YouTube channel ◦ Deep link to youtube | Deep links to church channel in YouTube app. | Mobile Dev | P1 - High | Not Started
| Promise & YouTube Video | 3.2.4 | Video archive ◦ Past 30 daily videos | Scrollable list of past videos. Tap to play. | Mobile Dev | P1 - High | Not Started
| Promise & YouTube Video | 3.2.5 | Video push notification ◦ Cloud function onCreate | FCM push sent when new video is published. | Backend Dev | P0 - Critical | Not Started
| Promise & YouTube Video | 3.2.6 | Admin: add daily video ◦ Admin portal validation | Paste YouTube video ID, validates via YouTube oEmbed API. | Backend Dev | P1 - High | Not Started

## Week 4
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| Events & Announcements | 4.1.1 | Calendar screen ◦ Horizontal weekly scrollable calendar | Selected day highlighted. Events for selected day listed. | Mobile Dev | P0 - Critical | Not Started
| Events & Announcements | 4.1.2 | Event list view ◦ Events list card view | Events displayed as cards with badge, title, time, venue, RSVP. | Mobile Dev | P0 - Critical | Not Started
| Events & Announcements | 4.1.3 | Event detail screen ◦ Full event page ◦ Map link | Full event details, Map link opens Google Maps, Add to Calendar. | Mobile Dev | P1 - High | Not Started
| Events & Announcements | 4.1.4 | RSVP functionality (SF Sync) ◦ Sync RSVP to Salesforce | Writes to Firestore, updates count. Toggles to 'Cancel RSVP'. | Mobile Dev | P0 - Critical | Not Started
| Events & Announcements | 4.1.5 | Event push notifications ◦ System reminders | System sends reminders 24hr and 1hr before event. | Backend Dev | P0 - Critical | Not Started
| Events & Announcements | 4.1.6 | Deep link from notification ◦ Linking config | Tapping notification opens exactly that event's screen. | Mobile Dev | P1 - High | Not Started
| Events & Announcements | 4.1.7 | Admin: create/edit events ◦ Admin portal form | Create/edit events. Auto-creates matching Salesforce Campaign. | Backend Dev | P0 - Critical | Not Started
| Events & Announcements | 4.2.1 | Announcements list screen ◦ Pinned shown at top | Scrollable feed. Title, body, image, timestamp, badge. | Mobile Dev | P1 - High | Not Started
| Events & Announcements | 4.2.2 | Announcement detail ◦ Full text | Full announcement with formatted text and share button. | Mobile Dev | P2 - Medium | Not Started
| Events & Announcements | 4.2.3 | Announcement push notification ◦ Segmented messaging | Admin sends targeted FCM notifications (All, Youth, Cell Group). | Backend Dev | P1 - High | Not Started
| Events & Announcements | 4.2.4 | Admin: create announcement ◦ RTE portal | Rich text editor, target segment selector, pin toggle. | Backend Dev | P1 - High | Not Started

## Week 5
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| Prayer Wall & Community | 5.1.1 | Prayer wall feed ◦ Infinite scroll pagination | Scrollable list of approved requests. 'I Prayed' button shown. | Mobile Dev | P0 - Critical | Not Started
| Prayer Wall & Community | 5.1.2 | Filter tabs ◦ All / Answered / Mine | Tab selection updates Firestore query results. | Mobile Dev | P1 - High | Not Started
| Prayer Wall & Community | 5.1.3 | Submit prayer request ◦ Form payload + Salesforce Case | Submits to admin queue. Cloud Function creates SF Case. | Mobile Dev | P0 - Critical | Not Started
| Prayer Wall & Community | 5.1.4 | I Prayed button ◦ Optimistic UI update | Transaction increments count. Button becomes filled. | Mobile Dev | P0 - Critical | Not Started
| Prayer Wall & Community | 5.1.5 | Notification: someone prayed ◦ Cloud Scheduler daily 6PM | Batched daily push: 'X people prayed for you today'. | Backend Dev | P2 - Medium | Not Started
| Prayer Wall & Community | 5.1.6 | Testimony / Prayer answered ◦ Close SF Case | Requester marks as Answered with testimony. Notifies members. | Mobile Dev | P1 - High | Not Started
| Prayer Wall & Community | 5.1.7 | Pastor response ◦ Private prayer response | Pastor issues private response. User receives notification. | Backend Dev | P1 - High | Not Started
| Prayer Wall & Community | 5.1.8 | Admin moderation panel ◦ Approve / Reject | Web portal shows pending queue. Pastor can moderate one-click. | Backend Dev | P0 - Critical | Not Started

## Week 6
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| Giving & SF Sync | 6.1.1 | Giving screen UI ◦ Category dropdown, preset chips | Mobile form UI matches giving wireframe exactly. | Mobile Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.1.2 | PhonePe SDK integration ◦ InitiateTransaction using sandbox | PhonePe PG SDK installed. Correct payload and response handled. | Mobile Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.1.3 | Payment initiation Cloud Function ◦ Unique transaction ID generation | Validates minimum amount. Creates pending order. | Backend Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.1.4 | PhonePe webhook handler ◦ SHA256 Verification | Verifies checksum. Idempotent check. Triggers SF sync on success. | Backend Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.1.5 | Payment success screen ◦ Animated checkmark | Displays success data natively: Amount, Checkmark, Download Receipt. | Mobile Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.1.6 | UPI QR code display ◦ Static QR string encoding | Shows generated UPI QR code as fallback option. | Mobile Dev | P1 - High | Not Started
| Giving & SF Sync | 6.2.1 | Create Opportunity in SF ◦ Opportunity creation mapping | Cloud function creates Salesforce Opportunity on PhonePe success. | Backend Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.2.2 | NPSP Soft Credit linking | Associate Opportunity with donor using Contact Role. | SF Admin | P1 - High | Not Started
| Giving & SF Sync | 6.2.3 | Recurring donation object | Creates NPSP Recurring Donation record for monthly choices. | Backend Dev | P2 - Medium | Not Started
| Giving & SF Sync | 6.2.4 | Giving history in app ◦ Profile Giving tab | Lists all successful transactions from Firestore. Date, category, amount. | Mobile Dev | P0 - Critical | Not Started
| Giving & SF Sync | 6.2.5 | PDF receipt generation ◦ Includes valid 80G tax stamp | Generates PDF via PDFKit, stored in Storage, delivered by email. | Backend Dev | P1 - High | Not Started

## Week 7
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| Admin Portal & Reports | 7.1.1 | Admin authentication/roles ◦ Custom Claims in Firebase Auth | Web portal login secured via Custom Claims (Super Admin, Pastor, Finance). | Backend Dev | P0 - Critical | Not Started
| Admin Portal & Reports | 7.1.2 | Dashboard overview ◦ Aggregated view | Shows aggregated metrics: daily view, count, stats from Salesforce. | Backend Dev | P1 - High | Not Started
| Admin Portal & Reports | 7.1.3 | Content management — Promises | CRUD interface. Export missing dates. CSV batch import support. | Backend Dev | P0 - Critical | Not Started
| Admin Portal & Reports | 7.1.4 | Content management — Videos | CRUD interface for youtube videos. Live preview validation. | Backend Dev | P0 - Critical | Not Started
| Admin Portal & Reports | 7.1.5 | Content management — Events | CRUD interface with standard fields + map linking + publish toggles. | Backend Dev | P0 - Critical | Not Started
| Admin Portal & Reports | 7.1.6 | Content management — Announcements | CRUD interface. Quill.js editor. Segments targeting. | Backend Dev | P1 - High | Not Started
| Admin Portal & Reports | 7.1.7 | Prayer moderation queue | Review pending requests. Handle logic visually. | Backend Dev | P0 - Critical | Not Started
| Admin Portal & Reports | 7.1.8 | Push notification broadcaster | Function to send FCM Multicast notifications segment-wise. | Backend Dev | P0 - Critical | Not Started
| Admin Portal & Reports | 7.1.9 | Giving admin dashboard | Table of all transactions with filters matching Salesforce. | Backend Dev | P1 - High | Not Started
| Admin Portal & Reports | 7.1.10 | Member directory | Table of registered app users. Deep links to Salesforce contact. | Backend Dev | P1 - High | Not Started
| Admin Portal & Reports | 7.2.1 | Giving summary report (SF) ◦ Grouped Opportunities by Month | SF report showing total amount and donor count per category. | SF Admin | P1 - High | Not Started
| Admin Portal & Reports | 7.2.2 | Event attendance report (SF) | SF Report: Campaign Members grouped by Campaign showing attendance. | SF Admin | P1 - High | Not Started
| Admin Portal & Reports | 7.2.3 | New members report (SF) | Contacts with Mobile App Source created last 30 days. | SF Admin | P2 - Medium | Not Started
| Admin Portal & Reports | 7.2.4 | Finance dashboard (SF) | SF Dashboard with bar chart, pie chart, and Goal gauge. | SF Admin | P1 - High | Not Started

## Week 8
Date | Phase | Task ID | Task / Requirement | Acceptance Criteria | Owner | Priority | Status
| QA & App Store Launch | 8.1.1 | Functional testing — Android | All 42 requirements verified on Android budget and mid-range devices. | QA | P0 - Critical | Not Started
| QA & App Store Launch | 8.1.2 | Functional testing — iOS | All requirements verified on iPhone. Minimum iOS 15. | QA | P0 - Critical | Not Started
| QA & App Store Launch | 8.1.3 | Payment flow testing | Full PhonePe payment journey robustly tested: success, failure, timeout. | QA | P0 - Critical | Not Started
| QA & App Store Launch | 8.1.4 | Push notification testing | All notification types delivered successfully. Deep links work. | QA | P0 - Critical | Not Started
| QA & App Store Launch | 8.1.5 | Offline mode testing | App gracefully handles airplane mode without crashing. | QA | P1 - High | Not Started
| QA & App Store Launch | 8.1.6 | Performance testing | App launch time < 3 seconds. Screens load < 1.5 seconds. | QA | P1 - High | Not Started
| QA & App Store Launch | 8.1.7 | Security testing | Firestore rules rigorously tested. Checksums secure. | Backend Dev | P0 - Critical | Not Started
| QA & App Store Launch | 8.1.8 | Accessibility testing | VoiceOver/TalkBack navigable. WCAG AA colors. | QA | P2 - Medium | Not Started
| QA & App Store Launch | 8.2.1 | Google Play Store — Internal | AAB uploaded to Play Console Internal track. Tested by 5 members. | Mobile Dev | P0 - Critical | Not Started
| QA & App Store Launch | 8.2.2 | Google Play Store — Prod | Privacy policy hosted, Content questionnaire, Store assets merged. Submitted. | Mobile Dev | P0 - Critical | Not Started
| QA & App Store Launch | 8.2.3 | Apple App Store — TestFlight | IPA uploaded to App Store Connect. Sent to 10 beta testers. | Mobile Dev | P0 - Critical | Not Started
| QA & App Store Launch | 8.2.4 | Apple App Store — Review submission | App submitted for App Store review with notes for nonprofit/PhonePe. | Mobile Dev | P0 - Critical | Not Started
| QA & App Store Launch | 8.2.5 | App Store listing assets | iOS and Android store screenshots and app trailer video finalized. | Designer | P1 - High | Not Started
| QA & App Store Launch | 8.3.1 | Admin portal training | 2-hour training session held. Loom recording and cheat sheet generated. | Backend Dev | P1 - High | Not Started
| QA & App Store Launch | 8.3.2 | Content pre-loading | Load 30 days of daily promises and 7 days of daily videos before launch. | SF Admin | P0 - Critical | Not Started
| QA & App Store Launch | 8.3.3 | WhatsApp launch announcement | Push out 1-pager with download links and QR to WhatsApp group. | Mobile Dev | P2 - Medium | Not Started
| QA & App Store Launch | 8.3.4 | Production monitoring | Firebase Crashlytics active with high crash velocity alerts. | Backend Dev | P1 - High | Not Started